## Sheet1
SAMPLE - UNIT BY UNIT WORK SCHEDULE
REVISED x/x/xxxx
[5 empty] | DOORS | [6 empty] | ENTRY FINISHES | [6 empty] | LIVING ROOM FINISHES | [8 empty] | KITCHEN FINISHES | [13 empty] | BATHROOM FINISHES | [13 empty] | BEDROOM FINISHES | [6 empty] | GENERAL UNIT
| ORIGINAL BUILDING ADDRESS | BUILDING-UNIT # | UNIT TYPE | DEMO UNIT CREATE NEW UFAS/A UNIT | REPLACE ENTRY DOOR w/ FRAME | REPAIR ENTRY DOOR w/FRAME | REPLACE INTERIOR DOORS | REPAIR INTERIOR DOORS / UNDERCUT DOORS | REPLACE BI-FOLD/SLIDING DOORS w/ SWINGING DOORS | REPLACE DOOR HARDWARE W/ VHDA APPROVED | NOTES: | REPLACE ENTRY FLOORING (VINYL PLANK) | REPAIR ENTRY FLOORING | REPLACE BASE / TRIM | REPAIR BASE / TRIM | REPAIR / PAINT WALLS SIGNIFICANT | REPAIR/PAINT WALLS MINIMAL | NOTES: | INSTALL / REPLACE CLOSET SHELVES | REPLACE UNIT SUBFLOORING | REPLACE UNIT FLOORING (VINYL PLANK) | REPAIR UNIT FLOORING | REPLACE BASE/TRIM | REPAIR BASE / TRIM | REPAIR / PAINT WALLS SIGNIFICANT | REPAIR/PAINT WALLS MINIMAL | NOTES: REPLACE ROD & SHELVES | REPLACE KITCHEN FLOORING (VINYL PLANK) | REPLACE BASE / TRIM | REPAIR BASE / TRIM | REPLACE KITCHEN CABINETS & COUNTERTOPS | REPLACE RANGE / NO ENERGY STAR LABEL | NEW RANGE HOOD | NEW UFAS/A RANGE | NEW RANGE FIRE SUPPRESSION | REPLACE KITCHEN SINK | NEW DISHWASHER | REPLACE REFRIGERATOR | REPAIR / PAINT WALLS MINIMAL | REMOVE/STORE/REINSTALL GARBAGE DISPOSAL | NOTES: | CREATE UFAS/A BATHROOM | REPLACE BATHROOM FLOORING (LVT OR SHEET VINYL) | REPLACE BASE / TRIM | REPLACE VANITY CABINET & COUNTERTOP | REPLACE VANITY MIRROR /REMOVE MEDICINE CABINET | REPLACE VANITY FAUCET / WATER SENSE | REPLACE BATHROOM ACCESSORIES | REPLACE SHOWERHEAD / FAUCET / VALVE | REPLACE TUB / SHOWER | REFINSH TILE WALLS / FLOORS / TUB | REPLACE TOILET / WATER SENSE | BATH FAN WIRED TO PRIMARY LIGHT w/ DELAYED TIMER | PAINT / REPAIR WALLS | NOTES: | REPLACE BEDROOM FLOORING (CARPET) | REPLACE BASE/TRIM | REPLACE BIFOLD DOORS | REPLACE LIGHT FIXTURES | REPAIR/PAINT WALLS | CLOSET ROD & SHELF (VES) | NOTES: | NEW HVAC UNIT, GRILLES, THERMOSTAT | REPLACE WATER HEATER | REPLACE CENTRAL HOT WATER BOILER | SEAL AROUND PME PENETRATIONS | NEW DEHUMIDIFICATION DRAIN / HOOKUPS | INFRASTRUCTURE FOR HIGH-SPEED INTERNET | PROVIDE EACH TENANT FREE HIGH SPEED INTERNET (WIRELESS) | REPLACE UNIT WINDOWS | REPLACE UNIT WINDOW BLINDS | CLEAN EXISTING DUCTWORK | REPLACE SMOKE DETECTORS / ADD BATTERIES | REPLACE COVER PLATES / OUTLETS / SWITCHES | REPLACE LIGHTING AS SCHEDULED | NOTES:
1 | [76 empty] | 1
2 | [76 empty] | 2
3 | [76 empty] | 3
4 | [76 empty] | 4
5 | [76 empty] | 5
6 | [76 empty] | 6
7 | [76 empty] | 7
8 | [76 empty] | 8
9 | [76 empty] | 9
10 | [76 empty] | 10
11 | [76 empty] | 11
12 | [76 empty] | 12
13 | [76 empty] | 13
14 | [76 empty] | 14
15 | [76 empty] | 15
16 | [76 empty] | 16
17 | [76 empty] | 17
18 | [76 empty] | 18
19 | [76 empty] | 19
20 | [76 empty] | 20
21 | [76 empty] | 21
22 | [76 empty] | 22
23 | [76 empty] | 23
24 | [76 empty] | 24
25 | [76 empty] | 25
26 | [76 empty] | 26
27 | [76 empty] | 27
28 | [76 empty] | 28
29 | [76 empty] | 29
30 | [76 empty] | 30
31 | [76 empty] | 31
32 | [76 empty] | 32
33 | [76 empty] | 33
34 | [76 empty] | 34
35 | [76 empty] | 35
36 | [76 empty] | 36
37 | [76 empty] | 37
38 | [76 empty] | 38
39 | [76 empty] | 39
40 | [76 empty] | 40
41 | [76 empty] | 41
42 | [76 empty] | 42
43 | [76 empty] | 43
44 | [76 empty] | 44
45 | [76 empty] | 45
46 | [76 empty] | 46
47 | [76 empty] | 47
48 | [76 empty] | 48
49 | [76 empty] | 49
50 | [76 empty] | 50
51 | [76 empty] | 51
52 | [76 empty] | 52
53 | [76 empty] | 53
54 | [76 empty] | 54
55 | [76 empty] | 55
56 | [76 empty] | 56
NOTES:
| Y = | IN SCOPE
| N = | NOT IN SCOPE